## SIQ-REV
Review ID | Date | File Name | ID Link | Reviewer(s) | Summary of Findings | Action Items / Comments | Status | Next Review Date | Git-Version
REV-001 | 2025-04-06 | SIQ Requirements |  | Ahmed | Recommend changing the ID naming convention for consistency. | SIQ ID Convention: Recommend using the format SIQ-User-01 for requirement IDs (e.g., SIQ-User-01, SIQ-Login-01) instead of just User-01 for consistency and clarity. | Done | 2025-04-10
REV-002 | 2025-04-06 | SIQ Requirements |  | Ahmed | Document does not include: 1) Option for users to submit feedback or reviews | SIQ Requirements: Please add the following questions to address feedback needs: • Feedback – Should users be allowed to submit feedback or reviews in addition to ratings? | Done | 2025-04-10

## CRS-REV
Review ID | Date | File Name | ID Link | Reviewer(s) | Summary of Findings | Action Items / Comments | Status | Next Review Date | Git-Version
REV-001 | 2025-04-10 | CRS_Travel_Advisor_Web_Application |  | Abdulkarim Abdo | Naming Convention sequencing all requirements together, this will cause problems separating each requirement work products. | CRS Naming Convention: naming should start from 000 for each item. so login and all other different requirements should begin with 000. | Done |  | CRS_V1.1
REV-002 | 2025-04-10 | CRS_Travel_Advisor_Web_Application |  | Abdulkarim Abdo | Missing some CRS requirements | CRS Missing Requirements: 1-Application will be Pc/Web Based only. 2-Each user will have a unique ID. | Done |  | CRS_V1.1
REV-003 | 2025-04-11 | CRS_Travel_Advisor_Web_Application |  | Abdulkarim Abdo | No Gaps. |  |  |  | CRS_V1.2

## PMP-REV
Review ID | Date | File Name | ID Link | Reviewer(s) | Summary of Findings | Action Items / Comments | Status | Next Review Date
REV-001 | 2025-04-10 | Travel Advisor PMP |  | Asmaa | Duplicate numbering found (two sections labeled "11") | Update section numbers to avoid confusion. Rename "Configuration Management" to Section 12. | Done | 2025-04-10
REV-002 | 2025-04-10 | Travel Advisor PMP |  | Asmaa | The repository link is broken across two lines, which may cause issues in access | Fix the link formatting. Place the complete URL on one line: GitHub Repo | Done | 2025-04-10
REV-003 | 2025-04-10 | Travel Advisor PMP |  | Asmaa | The WBS lacks granularity in Testing sections | Break down testing into types (functional, regression, etc.) | Done | 2025-04-10
REV-004 | 2025-04-10 | Travel Advisor PMP |  | Asmaa | No gaps |  | Done | 2025-04-10
REV-005 | 2025-04-14 | Travel Advisor PMP |  | Omar | Review Strategy section is missed. | Consider including a clear and concise outline of how the review process will be conducted | Done
REV-006 | 2025-04-14 | Travel Advisor PMP |  | Omar | Problem Resolution Management section is missed. | Identify the problem, when did it happen, who is involved and its status during project lifecycle. | Done
REV-007 | 2025-04-14 | Travel Advisor PMP |  | Omar | Configuration Items List is missed. | Consider including Document name, Version, Link, Status. | Done
REV-008 | 2025-04-14 | Travel Advisor PMP |  | Omar | Change Management Section needs some editing. | Who approve the changed? Where to perform impact analysis? | Done
REV-009 | 2025-04-14 | Travel Advisor PMP |  | Omar | Naming convention needs some edits. | Please ensure that all files, names, and IDs follow a specific and standardized format along the project | Done
REV-010 | 2025-04-14 | Travel Advisor PMP |  | Omar | Change Request section is missed. | Consider including a Change Request section to document any changes made during the project and how they were handled. | Done
REV-011 | 2025-04-14 | Travel Advisor PMP |  | Omar | Risk Register section is missed. | editing to ensure all identified risks are clearly described, assessed with its impact , and updated with appropriate response plans and owners | Done

## SRS-REV
Review ID | Date | File Name | ID Link | Reviewer(s) | Summary of Findings | Action Items / Comments | Status | Next Review Date
REV-001 | 2025-04-20 | CRS_TravelAdvisor_webapplication | Registration | mohsen | cconfimmation password is missed | make sure that the comfirmation password is the same password in password field and if its different a error message is display | Done | 2025-04-20
REV-002 | 2025-04-21 | CRS_Travel_Advisor_Web_Application | Login | Abdulkarim | SRS-Login-11 and SRS-Login-12 are identical | Delete the duplication or correct it if you meant anything else. | Done | 2025-04-22
REV-003 | 2025-04-22 | CRS_Travel_Advisor_Web_Application | Gallery | mohsen |  | no gaps
REV-004 | 2025-04-23 | CRS_Travel_Advisor_Web_Application | Login | Abdulkarim | SRS-Login-8 missing some information. | ▪should specify a message appearing to inform the user of how many trials left for him before being blocked also specify the error message. ▪Specify the length of the valid email to be 255 characters. ▪Specify the accepted special characters. | POSTPONED
REV-005 | 2025-04-23 | CRS_Travel_Advisor_Web_Application | Rate | Caroline | SRS-Rate-01 is missing location of the rate option. | The rating should be visible in user's history
REV-006 | 2025-04-23 | CRS_Travel_Advisor_Web_Application | Platform | Caroline |  | no gaps
REV-007 | 2015-04-23 | CRS_Travel_Advisor_Web_Application | Admin | Caroline |  | no gaps
REV-008 | 2015-04-24 | CRS_Travel_Advisor_Web_Application | User Feature | Ahmed |  | no gaps
REV-009 | 2015-04-24 | CRS_Travel_Advisor_Web_Application | Booking | Mohsen |  | no gaps
REV-010 | 2025-04-24 | CRS_Travel_Advisor_Web_Application | Review Strategy | Mohsen |  | no gaps

## Design-REV
Review ID | Date | File Name | ID Link | Reviewer(s) | Summary of Findings | Action Items / Comments | Status | Next Review Date
REV-001 | 2025-04-24 | Design/Wireframe |  | Mohsen abdelkereem |  | No Gaps

## TC-REV
Review ID | Date | File Name | ID Link | Reviewer(s) | Summary of Findings | Action Items / Comments | Status | Next Review Date
REV-001 | 2025-04-23 | TC_Travel_Advisor_Web_Application |  | Abdulkarim | some duplications and invalid test cases. | ▪TC-Login-06 : precondition should be "User have a Registered Account" also should specify how many trials left. ▪TC-Login-12 :should be deleted invalid test case (2 negative scenarios) ▪TC-Login-13 : precondition should be "user must have a locked account for 10 minutes" ▪TC-Login-13 : result should be redirection to home page as it's a successful login. ▪TC-Login-15 should be deleted : will block the empty test cases, also not specified in requirements. ▪TC-Login-16 :should specify the length of the email from the requriments. ▪TC-Login-17 : should specify the accepted special chars from the requriments. ▪TC-Login-14 and TC-Login-1 are duplicated, delete 14. ▪TC-Login-18 and TC-Login-8 are duplicated , delete 18.