## planning and status
Project Name | Travel advisor | [5 empty] | Release #2 Planning
Team Members | Mohamed Mohsen (PM) | [5 empty] | Start Date |  |  |  | End Date
| Ahmed abdelrahman | [5 empty] | 2025-12-04 |  |  |  | 26/4/2025
| Abdelkarim | [5 empty] | Deliverables
| Moaz | [5 empty] | SRS - Test Cases - PM Taskes - Release #1 comments fixing(pmp) - Wireframe
Caroline
| Asmaa | [5 empty] | Customer: yousef |  |  |  | Coach: Omar
Work package ID |  | Work package Name |  |  | Task ID |  | Task Name |  | Owner |  | Time |  | Reviewer |  | Time | Status | percentage
WP_1 |  | SRS |  |  | SRS_FR_01 |  | SRS Login |  | Ahmed |  | 2.5H |  | Mohsen |  | 1H | Done | 100%
[5 empty] | SRS_FR_02 |  | SRS Registration |  | Moaz |  | 3.5H |  | Mohsen |  | 1H | Done
[5 empty] | SRS_FR_03 |  | SRS Rate |  | Asmaa |  | 1H |  | Caroline |  | 30MIN | Done
[5 empty] | SRS_FR_04 |  | SRS Admin |  | Abdulkarim |  | 1H |  | Caroline |  | 30MIN | Done
[5 empty] | SRS_FR_05 |  | SRS Booking |  | Asmaa |  | 1H |  | Mohsen |  | 30MIN | Done
[5 empty] | SRS_FR_06 |  | SRS Gallery |  | Ahmed |  | 1H |  | Abdulkarim |  | 30MIN | Done
[5 empty] | SRS_FR_07 |  | SRS User |  | Abdulkarim |  | 1H |  | Ahmed |  | 30MIN | Done
[5 empty] | SRS_FR_08 |  | SRS Platform |  | Abdulkarim |  | 1H |  | Caroline |  | 30MIN | Done
Work package ID |  | Work package Name |  |  | Task ID |  | Task Name |  | Owner |  | Time |  | Reviewer |  | Time | Status | percentage
WP_2 |  | TC |  |  | TC_FR_01 |  | TC Login |  | Ahmed |  | 2.5H |  | Mohsen |  | 1H | Inprogress | 20%
[5 empty] | TC_FR_02 |  | TC Registration |  | Moaz |  | 3.5H |  | Mohsen |  | 1H | Inprogress
[5 empty] | TC_FR_03 |  | TC Rate |  | Asmaa |  | 1H |  | Caroline |  | 30MIN | Inprogress
[5 empty] | TC_FR_04 |  | TC Admin |  | Abdulkarim |  | 1H |  | Caroline |  | 30MIN | Inprogress
[5 empty] | TC_FR_05 |  | TC Booking |  | Asmaa |  | 1H |  | Mohsen |  | 30MIN | Inprogress
[5 empty] | TC_FR_06 |  | TC Gallery |  | Ahmed |  | 2H |  | Abdulkarim |  | 30MIN | Inprogress
[5 empty] | TC_FR_07 |  | TC User |  | Abdulkarim |  | 1H |  | Ahmed |  | 30MIN | Inprogress
[5 empty] | TC_FR_08 |  | TC Platform |  | Abdulkarim |  | 1H |  | Caroline |  | 30MIN | Inprogress
Work package ID |  | Work package Name |  |  | Task ID |  | Task Name |  | Owner |  | Time |  | Reviewer |  | Time | Status | percentage
WP_3 |  | PMP_CPMMENTS |  |  | PMP_COM_01 |  | CHr template &discreption on PMP |  | Mohsen |  | 1H |  | Asmaa |  | 30min | Done | 90%
[5 empty] | PMP_COM_02 |  | Naming convention |  | Ahmed |  | 1H |  | Caroline |  | 30min | Done
[5 empty] | PMP_COM_03 |  | CIL template |  | Moaz |  | 30MIN |  | Asmaa |  | 10min | Done
[5 empty] | PMP_COM_04 |  | CM |  | Ahmed |  | 1H |  | Mohsen |  | 15min | Done
[5 empty] | PMP_COM_05 |  | Version history |  | Asmaa |  | 1H |  | Mohsen |  | 15min | Done
[5 empty] | PMP_COM_06 |  | Risk register |  | Moaz |  | 1H |  | Mohsen |  | 15min | Done
[5 empty] | PMP_COM_07 |  | Review strategy |  | Caroline |  | 1H |  | Mohsen |  | 15min | Done
[5 empty] | PMP_COM_08 |  | CIL on PMP |  | Ahmed |  | 1H |  | Asmaa |  | 30min | Done
[5 empty] | PMP_COM_09 |  | Critical risk |  | Abdulkarim |  | 1H |  | Ahmed |  | 30min | Inprogress
[5 empty] | PMP_COM_10 |  | Problem Resolution |  | Caroline |  | 1.5H |  | Abdulkarim |  | 30min | Done
Work package Name |  | Task ID |  | Task Name |  | Owner |  | Time |  | Reviewer |  | Time |  | Status | percentage
Wireframe |  | WF_01 |  | Making wireframe |  | Asmaa |  | 5H |  | Mohsen |  | 1H |  | Inprogress | 60%
[10 empty] | Abulkarim |  | 1H
Work package ID |  | Work package Name |  |  | Task ID |  | Task Name |  | Owner |  | Time |  | Status | percentage
WP_5 |  | PMP review |  |  | PMP_REV_01 |  | Making PMP review |  | Caroline |  | 2h |  | Done | 100%
Work package ID |  | Work package Name |  |  | Task ID |  | Task Name |  | Owner |  | Time |  | Status | percentage
WP_6 |  | PM Tasks |  |  | PM_TK_01 |  | Release planing |  | Mohsen |  | 1H |  | Done | 100%
Done
[5 empty] | PM_TK_02 |  | Creating backlig |  | Mohsen |  | 1H |  | Done
[5 empty] | PM_TK_03 |  | Assigniing tasks |  | Mohsen |  | 1H |  | Done
[5 empty] | PM_TK_04 |  | project status report |  | Mohsen |  | 1H |  | Done
|  | Total Task | Done | Inprogress
|  | 32 | 22Task- 65.7% | 10Task- 31.25%
.

## estimation
Team Member | Availability | Planned | Actual
Mohamed Mohsen | 20H | 14H | 12H
Ahmed Abdelrahman | 20H | 14H | 12H
Abdulkarim | 20H | 14H | 12H
Moaz | 20H | 14H | 11H
Asmaa | 20H | 14H | 10H
Caroline | 11H | 7H | 4H
Total | 111H | 77H | 61H