## planning and status
Project Name | Travel advisor | [7 empty] | Release #5 Planning
Team Members | Mohamed Mohsen (PM) | [7 empty] | Start Date |  |  |  | End Date
| Ahmed abdelrahman | [7 empty] | 2025-10-05 |  |  |  | 17/5/2025
| Abdelkarim | [7 empty] | Deliverables
| Moaz | [7 empty] | full tested software - comments from last release - PM Tasks
Caroline
| Asmaa | [7 empty] | Customer: yousef |  |  |  | Coach: Omar
Work package ID |  | Work package Name |  |  | Task ID | Task Name |  | Owner |  | Time |  | Reviewer |  | Time |  |  | Status | percentage
WP_1 |  | backend |  |  | admin panel | admin panel |  | asmaa |  | 4h |  | moaz |  | 2h
[5 empty] | booking | booking |  | asmaa |  | 5h |  | abdelkrim |  | 2h
Work package ID |  | Work package Name |  |  | Task ID | Task Name |  | Owner |  | Time |  | Reviewer |  | Time |  |  | Status | percentage
WP_2 |  | TC_Execution |  |  | REG | making reg |  | moaz |  | 3 |  | abdelkrim |  | 1H
[5 empty] | LOGIN | making login |  | ahmed |  | 3 |  | mohsen
[5 empty] | BOOKING | making booking |  | caroline |  | 3 |  | abdelkrim |  | 1H
[5 empty] | GALLERY | gallery |  | caroline |  | 2 |  | ahmed |  | 1H
[5 empty] | ADMIN | admin |  | caroline |  | 2 |  | ahmed |  | 1H
[5 empty] | RATE | rate |  | moaz |  | 2 |  | asmaa |  | 1H
|  | Work package ID |  |  | Work package Name |  | Task ID |  | Task Name |  | Owner |  | Time |  | Status | percentage
|  | WP_3 |  |  | PM Tasks |  | PM_TK_01 |  | Release planing |  | Mohsen |  | 1H
[7 empty] | PM_TK_02 |  | Creating backlog |  | Mohsen |  | 1H
[7 empty] | PM_TK_03 |  | Assigniing tasks |  | Mohsen |  | 1H
[7 empty] | PM_TK_04 |  | project status report |  | Mohsen |  | 1H
[7 empty] | PM_TK_05 |  | test strategy |  | Mohsen |  | 1H
|  | Total Task | Done | Inprogress
13

## estimation
Team Member | Availability | Planned | Actual
Mohamed Mohsen | 10 | 9
Ahmed Abdelrahman | 11 | 10
Abdulkarim | 12 | 11
Moaz | 10 | 9
Asmaa | 13 | 13
Caroline | 13 | 12
Total | 69 | 64

## indicators
SIQ | 26
CRS | 11
SRS | 44
TC PASS
TC FAIL
Total executed
TC | 67