## planning and status
Project Name | Travel advisor | [7 empty] | Release #5 Planning
Team Members | Mohamed Mohsen (PM) | [7 empty] | Start Date |  |  |  | End Date
| Ahmed abdelrahman | [7 empty] | 2025-10-05 |  |  |  | 17/5/2025
| Abdelkarim | [7 empty] | Deliverables
| Moaz | [7 empty] | Executing Test Case -Ccomments from last release - PM Tasks
Caroline
| Asmaa | [7 empty] | Customer: yousef |  |  |  | Coach: Omar
Work package ID |  | Work package Name |  |  | Task ID | Task Name |  | Owner |  | Time |  | Reviewer |  | Time |  |  | Status | percentage
WP_1 |  | backend |  |  | admin panel | admin panel |  | Ahmed |  | 4h |  | abdelkrim |  | 2h |  |  | done | 100%
[5 empty] | booking | booking |  | Ahmed |  | 5h |  | abdelkrim |  | 2h |  |  | done
[5 empty] | Rate | Rate |  | moaz |  | 5h |  | abdelkrim |  | 2h |  |  | done
Work package ID |  | Work package Name |  |  | Task ID | Task Name |  | Tester |  | Time |  | Developer |  | Time |  |  | Status | percentage
WP_2 |  | TC_Execution |  |  | REG | execute reg |  | asmaa , caroline |  | 3 |  | moaz |  | 1H |  |  | done | 100%
[5 empty] | LOGIN | execute login |  | asmaa |  | 3 |  | ahmed |  | 1H |  |  | done
[5 empty] | BOOKING | execute booking |  | caroline |  | 3 |  | asmaa |  | 1H |  |  | done
[5 empty] | GALLERY | execute gallery |  | caroline |  | 2 |  | asmaa |  | 1H |  |  | done
[5 empty] | ADMIN | execute admin |  | caroline |  | 2 |  | asmaa |  | 1H |  |  | done
[5 empty] | RATE | execute rate |  | moaz |  | 2 |  | moaz |  | 1H |  |  | done
|  | Work package ID |  |  | Work package Name |  | Task ID |  | Task Name |  | Owner |  | Time |  | Status | percentage
|  | WP_3 |  |  | PM Tasks |  | PM_TK_01 |  | Release planing |  | Mohsen |  | 1H |  | done | 100%
done
[7 empty] | PM_TK_02 |  | Creating backlog |  | Mohsen |  | 1H |  | done
[7 empty] | PM_TK_03 |  | Assigniing tasks |  | Mohsen |  | 1H |  | done
[7 empty] | PM_TK_04 |  | project status report |  | Mohsen |  | 1H |  | done
[7 empty] | PM_TK_05 |  | Indicators sheet |  | Mohsen |  | 1H |  | done
[7 empty] | PM_TK_06 |  | test strategy |  | Mohsen |  | 1H |  | done
Work package ID |  | Work package Name |  |  | Task ID | Task Name |  | Owner |  | Time |  | Reviewer |  | Time |  |  | Status | percentage
WP_4 |  | RTM |  |  | RTM | making RTM |  | Abdelkrim |  | 5h |  | mohsen |  | 2h |  |  | done | 100%
|  | Total Task | Done | Inprogress
15

## estimation
Team Member | Availability | Planned | Actual
Mohamed Mohsen | 10 | 9 | 10
Ahmed Abdelrahman | 11 | 10 | 11
Abdulkarim | 12 | 11 | 13
Moaz | 10 | 9 | 10
Asmaa | 12 | 11 | 9
Caroline | 12 | 12 | 13
Total | 67 | 62 | 66

## indicators
SIQ | 26
CRS | 12
SRS | 57
TC PASS | 61
TC FAIL | 13
Total executed | 74
TC | 83