## planning and status
Project Name | Travel advisor | [7 empty] | Release #3 Planning
Team Members | Mohamed Mohsen (PM) | [7 empty] | Start Date |  |  |  | End Date
| Ahmed abdelrahman | [7 empty] | 26/4/2025 |  |  |  | 2025-02-05
| Abdelkarim | [7 empty] | Deliverables
| Moaz | [7 empty] | frontend - backend - database (development)
Caroline
| Asmaa | [7 empty] | Customer: yousef |  |  |  | Coach: Omar
Work package ID |  | Work package Name |  |  | Task ID | Task Name |  | Owner |  | Time |  | Reviewer |  | Time |  |  |  | Status | percentage
WP_1 |  | Front development |  |  | FE_FR_01 | Login feature |  | Asmaa |  | 5H |  | Mohsen |  | 1H
[5 empty] | FE_FR_02 | Registration feature |  | moaz |  | 5H |  | Asmaa |  | 1H
[5 empty] | FE_FR_03 | Rate feature |  | Ahmed |  | 5H |  | asmaa |  | 1H
[5 empty] | FE_FR_04 | Admin feature |  | abdelkrim |  | 5H |  | Ahmed |  | 1H
[5 empty] | FE_FR_05 | Gallery feature |  | caroline |  | 5H |  | asmaa |  | 1H
|  | Work package ID |  |  | Work package Name |  | Task ID |  | Task Name |  | Owner |  | Time |  |  |  | Status | percentage
|  | WP_2 |  |  | PM Tasks |  | PM_TK_01 |  | Release planing |  | Mohsen |  | 1H
[7 empty] | PM_TK_02 |  | Creating backlog |  | Mohsen |  | 1H
[7 empty] | PM_TK_03 |  | Assigning tasks |  | Mohsen |  | 1H
[7 empty] | PM_TK_04 |  | project status report |  | Mohsen |  | 1H
|  | Work package ID |  |  | Work package Name |  | Task ID |  | Task Name |  | Owner |  | Time |  | reviewer | time | Status | percentage
|  | WP_3 |  |  | BackEnd develop |  | BE_FR_01 |  | Login feature |  | asmaa / abdlkrem |  | 2H |  | caroline | 1H
[7 empty] | BE_FR_02 |  | Registration feature |  | moaz |  | 2H |  | caroline | 1H
[7 empty] | BE_FR_03 |  | Rate feature |  | ahmed |  | 2H |  | caroline | 1H
[7 empty] | BE_FR_04 |  | Admin feature |  | Mohsen |  | 2H |  | caroline | 1H
[7 empty] | BE_FR_05 |  | Gallery feature |  | moaz |  | 2H |  | caroline | 1H
|  | Total Task | Done | Inprogress
14

## estimation
Team Member | Availability | Planned | Actual
Mohamed Mohsen | 10H | 10H
Ahmed Abdelrahman | 10H | 10H
Abdulkarim | 10H | 10H
Moaz | 10H | 10H
Asmaa | 10H | 10H
Caroline | 10H | 10H
Total | 60H | 60H

## indicators
SIQ | 26
CRS | 11
SRS | 44
TC | 67