## SIQ-REV
Review ID | Date | File Name | ID Link | Reviewer(s) | Summary of Findings | Action Items / Comments | Status | Next Review Date | Git-Version
REV-001 | 2025-04-06 | SIQ Requirements |  | Ahmed | Recommend changing the ID naming convention for consistency. | SIQ ID Convention: Recommend using the format SIQ-User-01 for requirement IDs (e.g., SIQ-User-01, SIQ-Login-01) instead of just User-01 for consistency and clarity. | Done | 2025-04-10
REV-002 | 2025-04-06 | SIQ Requirements |  | Ahmed | Document does not include: 1) Option for users to submit feedback or reviews | SIQ Requirements: Please add the following questions to address feedback needs: • Feedback – Should users be allowed to submit feedback or reviews in addition to ratings? | Done | 2025-04-10

## CRS-REV
Review ID | Date | File Name | ID Link | Reviewer(s) | Summary of Findings | Action Items / Comments | Status | Next Review Date | Git-Version
REV-001 | 2025-04-10 | CRS_Travel_Advisor_Web_Application |  | Abdulkarim Abdo | Naming Convention sequencing all requirements together, this will cause problems separating each requirement work products. | CRS Naming Convention: naming should start from 000 for each item. so login and all other different requirements should begin with 000. | Done |  | CRS_V1.1
REV-002 | 2025-04-10 | CRS_Travel_Advisor_Web_Application |  | Abdulkarim Abdo | Missing some CRS requirements | CRS Missing Requirements: 1-Application will be Pc/Web Based only. 2-Each user will have a unique ID. | Done |  | CRS_V1.1
REV-003 | 2025-04-11 | CRS_Travel_Advisor_Web_Application |  | Abdulkarim Abdo | No Gaps. |  |  |  | CRS_V1.2

## PMP_REV
Review ID | Date | File Name | ID Link | Reviewer(s) | Summary of Findings | Action Items / Comments | Status | Next Review Date
REV-001 | 2025-04-10 | Travel Advisor PMP |  | Asmaa | Duplicate numbering found (two sections labeled "11") | Update section numbers to avoid confusion. Rename "Configuration Management" to Section 12. | Done | 2025-04-10
REV-002 | 2025-04-10 | Travel Advisor PMP |  | Asmaa | The repository link is broken across two lines, which may cause issues in access | Fix the link formatting. Place the complete URL on one line: GitHub Repo | Done | 2025-04-10
REV-003 | 2025-04-10 | Travel Advisor PMP |  | Asmaa | The WBS lacks granularity in Testing sections | Break down testing into types (functional, regression, etc.) | Done | 2025-04-10
REV-004 | 2025-04-10 | Travel Advisor PMP |  | Asmaa | No gaps |  | Done | 2025-04-10
Rev-005 | 2025-04-05 | CRS_TravelAdvisor_webapplication |  | mohsen | No gaps |  | Done

## SRS_REV
Review ID | Date | File Name | ID Link | Reviewer(s) | Summary of Findings | Action Items / Comments | Status | Next Review Date
Rev-001 | 2025-04-20 | SRS_TravelAdvisor_webapplication | login | mohsen | cconfimmation password is missed | make sure that the comfirmation password is the same password in password field and if its different a error message is display