## planning and status
Project Name | Travel advisor | [7 empty] | Release #3 Planning
Team Members | Mohamed Mohsen (PM) | [7 empty] | Start Date |  |  |  | End Date
| Ahmed abdelrahman | [7 empty] | 26/4/2025 |  |  |  | 2025-02-05
| Abdelkarim | [7 empty] | Deliverables
| Moaz | [7 empty] | Design - ERD -PM Tasks
Caroline
| Asmaa | [7 empty] | Customer: yousef |  |  |  | Coach: Omar
Work package ID |  | Work package Name |  |  | Task ID | Task Name |  | Owner |  | Time |  | Reviewer |  | Time |  |  |  | Status | percentage
WP_1 |  | Design |  |  | D_FR_01 | Design Login |  | Asmaa /abdelkrim |  | 7H |  | Mohsen |  | 1H |  |  |  | inprogress | 50%
[5 empty] | D_FR_02 | Design Registration |  | moaz/caroline |  | 7H |  | Abdelkrim |  | 1H |  |  |  | in progress
[5 empty] | D_FR_03 | Design Rate |  | caroline |  | 7H |  | asmaa |  | 1H |  |  |  | Done
[5 empty] | D_FR_04 | Design Admin |  | Moaz |  | 7H |  | Ahmed |  | 1H |  |  |  | in progress
[5 empty] | D_FR_05 | Design Gallery |  | asmaa |  | 7H |  | Mohsen |  | 1H |  |  |  | Done
Work package ID |  | Work package Name |  |  | Task ID | Task Name |  | Owner |  | Time |  | Reviewer |  | Time |  |  |  | Status | percentage
WP_2 |  | DataBase |  |  | ERD_01 | Mking DB |  | Ahmed |  | 2H |  | Abdelkrim |  | 1H |  |  |  | Done | 100%
|  | Work package ID |  |  | Work package Name |  | Task ID |  | Task Name |  | Owner |  | Time |  |  |  | Status | percentage
|  | WP_3 |  |  | PM Tasks |  | PM_TK_01 |  | Release planing |  | Mohsen |  | 1H |  |  |  | Done | 100%
[7 empty] | PM_TK_02 |  | Creating backlog |  | Mohsen |  | 1H |  |  |  | Done
[7 empty] | PM_TK_03 |  | Assigniing tasks |  | Mohsen |  | 1H |  |  |  | Done
[7 empty] | PM_TK_04 |  | project status report |  | Mohsen |  | 1H |  |  |  | Done
|  | Work package ID |  |  | Work package Name |  | Task ID |  | Task Name |  | Owner |  | Time |  | reviewer | time | Status | percentage
|  | WP_4 |  |  | UI Design |  | UI_TK_01 |  | making ui design |  | Asmaa |  | 2H |  | mohsen | 1H | Done | 100%
|  | Total Task | Done | Inprogress
|  | 11 | 8 | 3

## estimation
Team Member | Availability | Planned | Actual
Mohamed Mohsen | 10H | 10 | 8
Ahmed Abdelrahman | 10H | 10 | 8
Abdulkarim | 10H | 10 | 8
Moaz | 10H | 10 | 8
Asmaa | 10H | 10 | 8
Caroline | 10H | 10 | 8
Total | 60H | 60H | 48H

## indicators
SIQ | 26
CRS | 11
SRS | 44
TC | 67